## Start here
Go-live and hypercare checklist
Go-live is the starting line, not the finish. What happens in the first few weeks decides whether people trust the system.
How to use it:
At the start of the final phase, give every item on Checklist an owner and a due date. Review it weekly with the project team, then daily in the last fortnight.
If something doesn't have an owner, it doesn't get done.
Agree who makes the go / no-go call, and on what evidence, before go-live week. Not at midnight on cutover day.
Use First fortnight to plan who is on the floor each shift, and Issue log from the first hour of production.
Key
Yellow cell, blue text | Your input. Replace the example values with your own.
Black text | Calculated. Leave these alone.
Green text | Pulled from another sheet.
Shopfloor Matters · shopfloormatters.com · Free to use and adapt. General information, not professional advice.

## Checklist
Readiness checklist
Status: Not started, In progress, Done, or N/A. The summary at the top updates as you go.
Items | 49 | Done | 0 | In progress | 0 | Not started | 49 | N/A | 0
Ready (done or N/A) | 0%
Area | Check | Owner | Due | Status | Evidence / notes | Must-have?
Scope and sign-off
Scope and sign-off | Go-live scope frozen and signed off: lines, processes, users and shifts |  |  | Not started |  | Yes
Scope and sign-off | To-be processes signed off by their owners |  |  | Not started |  | Yes
Scope and sign-off | Open change requests decided: in, deferred or rejected, with a reason |  |  | Not started |  | Yes
Scope and sign-off | Go / no-go decision-maker and criteria agreed in writing |  |  | Not started |  | Yes
Master data
Master data | Materials, BOMs, routings and work centres checked against the shopfloor |  |  | Not started |  | Yes
Master data | Routings use real cycle times, not planning estimates |  |  | Not started |  | Yes
Master data | Opening stock and WIP counted and loaded |  |  | Not started |  | Yes
Master data | Users, roles and skills loaded and access tested for each role |  |  | Not started |  | Yes
Master data | Quality plans, specs and limits loaded and checked by quality |  |  | Not started |  | Yes
Master data | Downtime and scrap reason codes agreed. Short lists people will use |  |  | Not started |  | Yes
Master data | Every label template printed on the real printers and scanned |  |  | Not started |  | Yes
Integration
Integration | ERP orders down and confirmations up, tested end to end with realistic volumes |  |  | Not started |  | Yes
Integration | Exceptions tested: changed orders, quantity differences, duplicate messages |  |  | Not started |  | Yes
Integration | Interface monitoring live, with a named owner for failed messages |  |  | Not started |  | Yes
Integration | Machine connectivity validated machine by machine against what the machine did |  |  | Not started |  | Yes
Integration | Recovery after a network drop tested. Nothing lost or duplicated |  |  | Not started |  | Yes
Testing
Testing | User acceptance signed off by operational users, including edge cases |  |  | Not started |  | Yes
Testing | Performance tested at the busiest shift, not a quiet afternoon |  |  | Not started |  | Yes
Testing | Site acceptance on the real shopfloor: real devices, real network, real gloves |  |  | Not started |  | Yes
Testing | Cutover rehearsed end to end, with timings |  |  | Not started |  | Yes
Testing | No severity 1 or 2 defects open. Workarounds written for the rest |  |  | Not started |  | Yes
Devices and infrastructure
Devices and infrastructure | Production environment sized, secured, backed up and monitored |  |  | Not started |  | Yes
Devices and infrastructure | Every device installed and tested at the point of use |  |  | Not started |  | Yes
Devices and infrastructure | Wi-Fi coverage tested everywhere it's needed, including the far corners |  |  | Not started |  | Yes
Devices and infrastructure | Backup and restore actually tested |  |  | Not started |  | Yes
Devices and infrastructure | Spare devices on hand |  |  | Not started |  | Yes
People and training
People and training | Super users trained deeply and released from their day job for hypercare |  |  | Not started |  | Yes
People and training | Every operator on every shift trained hands-on, nights and weekends included |  |  | Not started |  | Yes
People and training | Training and quick guides in the languages people speak |  |  | Not started |  | Yes
People and training | Supervisors trained on dashboards, approvals and deviations |  |  | Not started |  | Yes
People and training | Administrators able to make small configuration changes |  |  | Not started |  | Yes
People and training | What changes explained role by role, not as 'digital transformation' |  |  | Not started |  | Yes
People and training | Known concerns heard and answered, with the sponsor visibly backing it |  |  | Not started |  | Yes
Hypercare and support
Hypercare and support | Hypercare plan: how long, who's on the floor each shift, where the war room is |  |  | Not started |  | Yes
Hypercare and support | Vendor or partner support booked, with people who know your configuration |  |  | Not started |  | Yes
Hypercare and support | One issue log, agreed severity definitions and a daily triage time |  |  | Not started |  | Yes
Hypercare and support | Escalation path published |  |  | Not started |  | Yes
Hypercare and support | Hypercare exit criteria agreed, so it ends on evidence, not a date |  |  | Not started |  | Yes
Cutover and rollback
Cutover and rollback | Cutover plan written hour by hour, with owners |  |  | Not started |  | Yes
Cutover and rollback | Cutover timed for a quieter period, not month end or peak season |  |  | Not started |  | Yes
Cutover and rollback | Decision made on in-flight orders: finish the old way or migrate |  |  | Not started |  | Yes
Cutover and rollback | Production plan eased for the first days |  |  | Not started |  | Yes
Cutover and rollback | Rollback criteria, deadline and procedure agreed and rehearsed |  |  | Not started |  | Yes
Cutover and rollback | Paper forms or the old system ready for the fallback period |  |  | Not started |  | Yes
KPIs and communication
KPIs and communication | Baseline KPIs captured before go-live, using fixed definitions |  |  | Not started |  | Yes
KPIs and communication | Morning meeting dashboard ready for day one |  |  | Not started |  | Yes
KPIs and communication | Every shift briefed in person on what changes and who to call |  |  | Not started |  | Yes
KPIs and communication | Leadership told what week one looks like: slower and messier at first |  |  | Not started |  | Yes
KPIs and communication | Benefits tracking owner and review dates set |  |  | Not started |  | Yes

## Go no-go
Go / no-go decision
Run this at the go / no-go meeting with the sponsor in the room. Every line needs evidence, not a feeling.
Question | Yes / No | Evidence | Who confirmed
Any must-have items on Checklist not done?
Any severity 1 or 2 defects open?
Acceptance signed off by operational users?
Cutover rehearsal completed inside the window?
Master data and opening stock spot-checked in the last 48 hours?
Every go-live shift trained, with super users rostered?
Hypercare and vendor support confirmed, with names?
Rollback ready, with a decision point agreed?
Baseline KPIs captured?
Must-have items on Checklist not yet done or N/A | 49
Suggested call | No-go, or go with written conditions
Decision (Go / Go with conditions / No-go)
Conditions, owners and dates
Signed by the sponsor, and date
A delayed go-live is uncomfortable for a week. A failed one costs you the operators' trust for months.

## First fortnight
The first fortnight on the floor
Who is where, every shift. Leaders on the shopfloor, not in the war room.
When | Focus | Day shift | Back shift | Night shift | Done?
Cutover | Run the rehearsed plan. First order released, first label printed, first confirmation in ERP.
Day 1 | Super users and project team on every shift, visible. Log every issue, however small. Fix quick ones the same day.
Days 2 and 3 | Daily triage of the issue log. Watch the interfaces under real load, and night shift especially.
Days 4 and 5 | Close the issues that erode trust first. Tell the floor what's been fixed.
End of week 1 | Review against exit criteria. Celebrate the first wins. Honest update to the steering group and the floor.
Week 2 | Fewer people on the floor if the log allows. Check the first reports against reality.
End of week 2 | Exit hypercare on evidence, or extend it on purpose. Start comparing KPIs with the baseline.

## Issue log
Hypercare issue log
One place for every issue. Severity 1 stops production, 2 has a painful workaround, 3 is an annoyance, 4 is a request.
# | Raised | Line / area | Shift | What happened | Severity | Owner | Status | Fix and date
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100