## Start here
MES business case template
Business cases get approved faster when they show four things clearly:
1. What the problems cost today, in money (Baseline).
2. What will improve, by how much and when (Benefits).
3. Realistic costs and timeline, including your own people, not just licences and services (Costs).
4. How the risk is managed: a clear rollout plan across every site, with milestones and measures (Rollout).
How to use it:
Fill in Baseline with numbers finance will recognise. Set deliberately modest improvements on Benefits. Fill in every cost line, then read Cash flow.
Make the case for every site as one programme: licences for all your sites, a template built on the first, and a clear plan for the rest.
The example values describe a fictional mid-size site so you can see how it works. They are not a forecast. Replace them all.
Every amount is in your own currency. Percentages are entered as percentages (35% not 0.35 is fine, Excel handles both).
Key
Yellow cell, blue text | Your input. Replace the example values with your own.
Black text | Calculated. Leave these alone.
Green text | Pulled from another sheet.
Shopfloor Matters · shopfloormatters.com · Free to use and adapt. General information, not professional advice.

## Baseline
Baseline: what the problems cost today
Your site as it is now, for the lines or area in scope. Ask finance for revenue, margin and material cost. Measure the rest on the floor for a week if you can.
Input | Value | Unit | Where to get it
Annual revenue from the lines in scope | 25000000 | currency / year | Finance. Sales value of what these lines make.
Contribution margin | 35% | % of revenue | Finance. Revenue minus variable costs.
Current OEE | 55% | % | Measured, not estimated. Manual OEE usually flatters you.
Share of extra output you could sell | 50% | % | Sales. 100% if demand exceeds capacity, 0% if not.
Annual material cost on these lines | 11000000 | currency / year | Finance or ERP.
Scrap and rework rate | 4% | % of material | Quality. Scrap value ÷ material consumed.
Hours a year spent on paper and re-keying | 9000 | hours / year | Time it: forms, typing up, meeting prep, finding records.
Loaded hourly rate | 32 | currency / hour | HR or finance. Wage plus on-costs.
Average inventory value (raw, WIP, finished) | 4000000 | currency | Finance.
Annual carrying cost of inventory | 20% | % of value | Finance. Capital, storage, obsolescence. 15% to 25% is common.
Annual maintenance spend on these lines | 1200000 | currency / year | Maintenance or finance. Labour, contractors and spares.
Cost of scrap and rework today | 440000
Cost of paper and re-keying today | 288000
Cost of carrying inventory today | 800000
Value of one OEE point (the 1% question) | 79545.4545
Note on B20: Revenue × (1 point ÷ current OEE) × share you can sell × contribution margin.

## Benefits
Benefits: what improves, and when
Set improvements at the modest end. A board trusts a case that under-promises. The ramp sets how much of the full benefit you bank each year while the system beds in.
Lever | Improvement | How it's measured | Full-year benefit | Note
Higher OEE (points gained) | 5 | OEE points | 397727.2727 | Uses the value of one OEE point from Baseline.
Less scrap and rework | 10% | % cut in today's scrap cost | 44000 | A 10% cut in scrap is a modest target.
Less paper and re-keying | 50% | % of today's paper hours removed | 144000 | Count only hours you'd really redeploy or stop paying for.
Lower inventory | 10% | % cut in average inventory | 80000 | Carrying cost saved. The one-off cash release is not counted.
Less reactive maintenance | 5% | % cut in maintenance spend | 60000 | From planned work replacing breakdowns.
Total full-year benefit |  |  | 725727.2727
| Year 1 | Year 2 | Year 3
Benefit ramp | 40% | 80% | 100%
Not counted here | Quality escapes avoided, audit time, customer retention, less firefighting. Mention them, but keep them out of the numbers.

## Costs
Costs: every line, including your own people
The internal team is the cost people forget. Name the people and the share of their time. Put contingency in on purpose, not as padding.
Cost line | Year 0 (setup) | Year 1 | Year 2 | Year 3 | Note
Software subscription or licences | 0 | 90000 | 90000 | 90000 | Subscription each year, or licences up front plus maintenance.
Implementation services | 250000 | 30000 | 0 | 0 | Partner or vendor services. Ask for the plan behind the number.
Hardware and devices | 80000 | 10000 | 10000 | 10000 | Tablets, terminals, scanners, printers, spares.
Connectivity and infrastructure | 60000 | 0 | 0 | 0 | Machine connectivity, network, Wi-Fi, edge.
Internal team | 150000 | 80000 | 40000 | 40000 | People × share of time × loaded cost. Project lead, super users, IT.
Training | 30000 | 10000 | 5000 | 5000 | Operators on every shift, super users, administrators.
Running and support | 0 | 25000 | 25000 | 25000 | Hosting, internal support, interface monitoring.
Contingency | 85500 | 36750 | 25500 | 25500
Contingency rate (applied to every year) | 15%
Total cost | 655500 | 281750 | 195500 | 195500

## Cash flow
Cash flow, payback and ROI
Three years, using the ramp on Benefits. Payback is the first year cumulative cash turns positive.
| Year 0 | Year 1 | Year 2 | Year 3
Benefit | 0 | 290290.9091 | 580581.8182 | 725727.2727
Cost | -655500 | -281750 | -195500 | -195500
Net cash flow | -655500 | 8540.9091 | 385081.8182 | 530227.2727
Cumulative | -655500 | -646959.0909 | -261877.2727 | 268350
Three-year benefit | 1596600
Three-year cost | 1328250
Three-year net benefit | 268350
Three-year ROI | 20.2%
Payback | Year 3
Cost of doing nothing, per year | 725727.2727 | Every year you wait, this is what stays on the table.

## Rollout
Rollout: how the risk is managed
The section boards read most closely. The programme covers every site. Each stage has a scope, a measure and a milestone, so progress is visible all the way.
Stage | Scope | Duration | Success measure | Milestone | Owner
1. First site | The whole site, starting with production and quality | 6 to 9 months | OEE up 3 points against baseline; scrap down 10% | First site live on every shift | Operations director
2. Template | Standard processes, master data rules, KPIs and screens from the first site | 2 to 3 months | Template signed off by the centre of excellence | Template ready for the next site | Programme lead
3. Remaining sites | Every other site, from the same template | 4 to 6 months per site | Go-live on time with under 10% local change; benefits on Benefits sheet reached | Each site live on every shift | Programme lead